## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sowmika | 2026-01-08 | Incorrect encoding of categorical features in the dataset | Sprint 1 | Self | Logical | correctly did the encoding of different type accordingly. | 2026-01-08 | Closed | Fixed
2 | Sowmika | 2026-01-18 | Missed feature engineering part identifying important features and downloading , saving the new updated dataset | Spint 2 | Self | Logical | Finshed reaining part and saved the dataset | 2026-01-19 | Closed | Resolved
3 | Sowmika | 2026-01-22 | noticed negative values in some model evaluation measures. | sprint 3 | Self | Maintainability | increased rows of dataset and error is fixed. | 2026-02-28 | Closed | Fixed
4 | Sowmika | 2026-02-04 | observed inputed features fields are nnot matching with inputed features of the ml mmodel. | sprint4 | Self | Logical | extracted the non inputed fields required for ml model from historical data. | 2026-02-04 | Closed | Resolved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others